## DASHBOARD
CONSTRUCTION PROJECT MANAGEMENT DASHBOARD
[Site Name] · [Project Name] · [Client] · Week: 18 / 2026 · All KPI values are live Excel formulas
KEY PERFORMANCE INDICATORS
OVERALL PROGRESS |  |  | OPEN ACTIONS |  |  | OVERDUE ACTIONS |  |  | OPEN / ESCALATED RISKS |  | OPEN NCRs
AVERAGE(Actual%) |  |  | COUNTIF: Open + Overdue |  |  | COUNTIF: status=Overdue |  |  | COUNTIF: Open+Escalated |  | COUNTIF: Open+In Progress
DISCIPLINE PROGRESS · Live via AVERAGEIF / COUNTIFS from Weekly Progress, Risk Register & Action Log
Discipline | Planned % | Actual % | Variance % | Status | Open Actions | Open Risks | Open NCRs | SPI (Actual/Planned)
Civil
Structural
Electrical
Mechanical
Instrumentation
Piping
HVAC
Scaffolding
RISK SUMMARY · COUNTIFS | [5 empty] | ACTION ITEM STATUS · COUNTIF / COUNTIFS |  |  |  |  | NCR TYPE BREAKDOWN · COUNTIFS
Level | Total | Open | Escalated | Closed |  | Status | Count | % of Total | Critical/High | Med/Low | NCR Type | Total | Open
High | [5 empty] | Open |  |  |  |  | Material
Medium | [5 empty] | In Progress |  |  |  |  | Workmanship
Low | [5 empty] | Overdue |  |  |  |  | Installation
Closed
MONTHLY BUDGET & EARNED VALUE SUMMARY · SUMIFS multi-criteria aggregation
Month | Budget Hours (SUMIFS) | Actual Hours (SUMIFS) | Hours Var | Earned Value (SUMIFS) | Planned Value (SUMIFS) | SV (EV−PV) | CPI (EV÷PV)
Feb-26
Mar-26
Apr-26
VISUAL ANALYTICS · Charts refresh automatically when data changes

## Weekly Progress
WEEKLY PROGRESS TRACKER — Construction Site
Manual entry: columns G (Planned %) and H (Actual %). Formula-driven: I (Variance = H−G) · K (Status = IF logic) · L (Responsible = XLOOKUP) — do not overwrite.
ID | Discipline | Activity Description | Location | Planned Start | Planned Finish | Planned % ↓ enter | Actual % ↓ enter | Variance % =H−G | Week | Status =IF formula | Responsible =XLOOKUP | Submitted | Comments
WP-001 | Civil | Excavation — Foundation Area B3 | Zone B | 2026-03-10 | 2026-04-20 | 100% | 100% |  | 18 |  |  | 2026-05-01
WP-002 | Civil | Concrete Pour — Pile Caps Grid 4–7 | Zone B | 2026-04-01 | 2026-04-28 | 80% | 75% |  | 18 |  |  | 2026-05-01
WP-003 | Civil | Backfill & Compaction Block C | Zone C | 2026-04-15 | 2026-05-10 | 40% | 35% |  | 18 |  |  | 2026-05-01
WP-004 | Structural | Steel Erection — Main Frame Level 1 | Building 1 | 2026-03-20 | 2026-05-05 | 90% | 95% |  | 18 |  |  | 2026-05-01
WP-005 | Structural | Secondary Steelwork — Mezzanine | Building 1 | 2026-04-10 | 2026-05-20 | 55% | 58% |  | 18 |  |  | 2026-05-01
WP-006 | Electrical | Cable Tray Installation — HV Zone | Substation | 2026-04-01 | 2026-05-15 | 60% | 55% |  | 18 |  |  | 2026-05-01
WP-007 | Electrical | LV Panel Wiring — Control Room | Ctrl Room | 2026-04-20 | 2026-05-30 | 25% | 20% |  | 18 |  |  | 2026-05-01
WP-008 | Mechanical | Equipment Setting — Pump Skids P1–P4 | Pump Hall | 2026-04-05 | 2026-05-10 | 70% | 72% |  | 18 |  |  | 2026-05-01
WP-009 | Mechanical | Crane Girder Installation | Warehouse | 2026-04-15 | 2026-05-25 | 40% | 38% |  | 18 |  |  | 2026-05-01
WP-010 | Instrumentation | Instrument Loop Drawing Review | All Areas | 2026-03-25 | 2026-04-30 | 95% | 90% |  | 18 |  |  | 2026-05-01
WP-011 | Instrumentation | Field Instrument Installation Ph.1 | Zone A | 2026-04-20 | 2026-06-15 | 20% | 18% |  | 18 |  |  | 2026-05-01
WP-012 | Piping | Piping Spool Fabrication | Fab Shop | 2026-03-01 | 2026-04-30 | 100% | 100% |  | 18 |  |  | 2026-05-01
WP-013 | Piping | Piping Installation — Process Area | Zone A | 2026-04-10 | 2026-06-01 | 45% | 48% |  | 18 |  |  | 2026-05-01
WP-014 | Piping | Hydrostatic Testing — Line P-101 | Zone A | 2026-04-25 | 2026-05-05 | 100% | 100% |  | 18 |  |  | 2026-05-01
WP-015 | HVAC | Duct Fabrication & Delivery | Fab Shop | 2026-03-20 | 2026-04-25 | 85% | 80% |  | 18 |  |  | 2026-05-01
WP-016 | HVAC | Duct Installation — Ventilation Sys A | Building 1 | 2026-04-20 | 2026-05-30 | 30% | 25% |  | 18 |  |  | 2026-05-01
WP-017 | Scaffolding | Erect Scaffolding — Vessel V-201 | Zone B | 2026-04-01 | 2026-04-15 | 100% | 100% |  | 18 |  |  | 2026-05-01
WP-018 | Scaffolding | Scaffolding Maintenance Inspection | All | 2026-05-01 | 2026-05-03 | 100% | 100% |  | 18 |  |  | 2026-05-01
ACTIVITY PROGRESS CHART · Planned vs Actual % per Activity
Note on I3: Variance % [FORMULA — do not edit] ──────────────────────────────── = Actual% − Planned% Positive (+) = Ahead of schedule Negative (−) = Behind schedule Colour scale: red → white → green
Note on K3: Status [FORMULA — do not edit] ──────────────────────────────── = IF(H≥1, 'Completed', IF(H−G > 3%, 'Ahead', IF(G−H > 3%, 'Behind', 'On Track'))) Muted badge colours applied via conditional formatting
Note on L3: Responsible [XLOOKUP — auto-filled] ──────────────────────────────── = XLOOKUP(Discipline, LookupTables!A:A, LookupTables!B:B) Auto-fills lead person from Lookup Tables. You can override this cell manually if needed.

## Risk Register
RISK REGISTER — Construction Project
Formula-driven: G (Score = Prob × Impact) · H (Level = IF nested) — enter only columns E and F to set risk level automatically.
Risk ID | Category | Risk Description | Discipline | Prob (1–5) | Impact (1–5) | Risk Score =E×F | Risk Level =IF formula | Mitigation Action | Risk Owner | Date Identified | Review Date | Status | Comments
RSK-001 | Safety | Working at height without valid scaffold inspection cert | Scaffolding | 4 | 5 |  |  | Weekly scaffold inspection; tag all approved access points | K. Lindqvist | 2026-03-15 | 2026-05-15 | Open
RSK-002 | Schedule | Concrete delivery delays due to road restrictions | Civil | 3 | 4 |  |  | Pre-order extra trucks; identify alternative delivery route | J. Hansen | 2026-03-20 | 2026-05-10 | Open
RSK-003 | Quality | Weld defects detected in structural steel connections | Structural | 2 | 5 |  |  | Increase NDE scope to 20%; assign dedicated QC inspector | M. Berg | 2026-04-01 | 2026-05-20 | Escalated
RSK-004 | Technical | Instrument loop testing failure — signal noise on TI-101 | Instrumentation | 3 | 3 |  |  | Replace shielded cables; verify earthing configuration | T. Eriksson | 2026-04-05 | 2026-05-05 | Open
RSK-005 | Cost | Material price escalation — copper cable +18% | Electrical | 3 | 3 |  |  | Lock prices via frame agreement; evaluate alternative suppliers | A. Nilsen | 2026-03-28 | 2026-05-28 | Open
RSK-006 | Environmental | Fuel spill risk near water body — Zone C | Civil | 2 | 4 |  |  | Install secondary containment; daily environmental officer check | K. Lindqvist | 2026-04-10 | 2026-05-30 | Open
RSK-007 | Schedule | Late delivery of critical pump P-201 from vendor | Mechanical | 4 | 3 |  |  | Expedite vendor; activate contractual penalty clause if >1 week | A. Nilsen | 2026-04-12 | 2026-05-12 | Open
RSK-008 | Contractual | Design change — revised P&ID impacting piping route | Piping | 2 | 3 |  |  | Issue formal change request; update schedule and cost estimate | S. Patel | 2026-04-18 | 2026-05-18 | Open
RSK-009 | Safety | Subcontractor personnel without site induction | All | 2 | 3 |  |  | Gate access control + daily induction records; revoke access on breach | L. Andersen | 2026-04-20 | 2026-06-01 | Mitigated
RSK-010 | Technical | Fire suppression system pressure test failure | Mechanical | 1 | 4 |  |  | Pre-test with water; specialist commissioning team on standby | A. Nilsen | 2026-04-22 | 2026-06-15 | Open
RSK-011 | Quality | Painting rework due to humidity beyond 85% spec | Structural | 2 | 2 |  |  | Monitor humidity; restrict painting to approved windows only | M. Berg | 2026-04-15 | 2026-05-15 | Mitigated
RSK-012 | Schedule | Permit delays for HV cable route crossing | Electrical | 1 | 2 |  |  | Engage authority early; submit permit 4 weeks in advance | M. Berg | 2026-04-25 | 2026-06-01 | Closed
RSK-013 | Cost | Scaffolding overhire duration beyond contract | Scaffolding | 1 | 2 |  |  | Weekly utilisation review; demobilise when work front closes | R. Kowalski | 2026-03-10 | 2026-05-01 | Closed
RSK-014 | Technical | HVAC unit dimension mismatch with building opening | HVAC | 1 | 3 |  |  | Review shop drawings vs. site measurement before delivery | L. Andersen | 2026-04-28 | 2026-05-28 | Open
RSK-015 | Environmental | Noise complaint from community during night work | Civil | 1 | 2 |  |  | Restrict noisy ops 07:00–22:00; notify community in advance | K. Lindqvist | 2026-04-30 | 2026-06-01 | Open
Note on G3: Risk Score [FORMULA = E × F — do not edit] ──────────────────────────────── = Probability × Impact 1–7 = Low (green heat-map) 8–14 = Medium (amber heat-map) 15–25 = High (red heat-map) Edit cols E and F; Score recalculates automatically.
Note on H3: Risk Level [FORMULA — do not edit] ──────────────────────────────── = IF(Score≥15, 'High', IF(Score≥8, 'Medium', 'Low')) Muted pastel badge applied automatically via conditional formatting.

## Action Item Log
ACTION ITEM LOG — Site Coordination Meetings
F (Responsible) = VLOOKUP · N (Days Overdue) = IF(AND(≠Closed, TODAY()>DueDate), TODAY()−DueDate, "") · Status/Priority use dropdown validation
Action ID | Source / Meeting | Date Raised | Action Description | Discipline | Responsible =VLOOKUP | Due Date | Priority | Status | % Done | Date Closed | Verified By | Comments | Days Overdue =IF/TODAY()
ACT-001 | Site Coord W17 | 2026-04-24 | Resolve concrete pour access conflict — Civil vs Piping Zone B | Civil |  | 2026-04-28 | High | Closed | 100% | 2026-04-27 | M. Berg
ACT-002 | Daily Standup W18 | 2026-04-27 | Submit updated cable installation schedule for approval by Project Engineer | Electrical |  | 2026-04-30 | High | Closed | 100% | 2026-04-29 | T. Eriksson
ACT-003 | Quality Mtg W17 | 2026-04-24 | Issue corrective action for weld rejection — NCR-007 structural connections | Structural |  | 2026-05-02 | Critical | In Progress | 60%
ACT-004 | Site Coord W18 | 2026-05-01 | Update risk register with new schedule risks from vendor delays | All |  | 2026-05-05 | Medium | Open | 0%
ACT-005 | Client Mtg W17 | 2026-04-23 | Prepare monthly progress report for Client review — May 2026 | All |  | 2026-05-07 | High | Open | 0%
ACT-006 | Daily Standup W18 | 2026-04-28 | Calibrate pressure gauges before hydrostatic test — Piping Line P-102 | Piping |  | 2026-04-30 | High | Closed | 100% | 2026-04-30 | A. Nilsen
ACT-007 | Safety Mtg W18 | 2026-04-29 | Conduct emergency evacuation drill before end of May | All |  | 2026-05-20 | Medium | Open | 0% |  | Coordinate HSE
ACT-008 | Quality Mtg W18 | 2026-04-30 | Review and close outstanding punchlist items — Structural Level 1 | Structural |  | 2026-05-09 | Medium | In Progress | 30%
ACT-009 | Site Coord W18 | 2026-05-01 | Confirm HVAC unit dimensions match building opening before delivery | HVAC |  | 2026-05-08 | High | Open | 0%
ACT-010 | Client Mtg W17 | 2026-04-23 | Issue revised programme baseline incorporating scope change SCR-012 | All |  | 2026-05-03 | Critical | Overdue | 80% |  | Awaiting design
ACT-011 | Daily Standup W19 | 2026-05-04 | Update SharePoint tracker — weekly discipline progress inputs for W19 | All |  | 2026-05-06 | Medium | Open | 0%
ACT-012 | Safety Mtg W17 | 2026-04-22 | Replace damaged scaffolding clips — Tag Red Zone 4 out of service immediately | Scaffolding |  | 2026-04-24 | Critical | Closed | 100% | 2026-04-24 | L. Andersen
ACT-013 | Quality Mtg W17 | 2026-04-24 | Submit material traceability certificates for steel batch SB-044 | Structural |  | 2026-04-28 | High | Closed | 100% | 2026-04-26 | M. Berg
ACT-014 | Site Coord W18 | 2026-05-01 | Validate instrument calibration data before loop testing | Instrumentation |  | 2026-05-12 | High | Open | 0%
ACT-015 | Client Mtg W18 | 2026-04-30 | Confirm milestone dates — re-baseline if necessary; client sign-off required | All |  | 2026-05-14 | High | Open | 0%
ACT-016 | Daily Standup W18 | 2026-04-28 | Resolve interface clash — mechanical skid vs. electrical conduit Zone A | Mechanical |  | 2026-05-02 | Medium | In Progress | 50% |  | 3D review needed
ACT-017 | Safety Mtg W18 | 2026-04-29 | Ensure all subcontractors complete updated Method Statement review | All |  | 2026-05-06 | High | Open | 0%
Formulas:
Days Overdue =IF/TODAY() = IF(AND([Status]<>"Closed",[Status]<>"On Hold",ISNUMBER([Due Date]),TODAY()>[Due Date]),TODAY()-[Due Date],"")
Note on F3: Responsible [VLOOKUP — auto-filled] ──────────────────────────────── = VLOOKUP(Discipline, LookupTables, 2, 0) Auto-fills the discipline lead from Lookup Tables. Override manually if the action owner is a different person.
Note on N3: Days Overdue [FORMULA — do not edit] ──────────────────────────────── = IF(AND(Status≠'Closed', Status≠'On Hold', ISNUMBER(DueDate), TODAY() > DueDate), TODAY() − DueDate, '') Updates automatically each time the file is opened. Red cell fill applied when value > 0.

## NCR Quality Tracker
NON-CONFORMANCE REPORT (NCR) & QUALITY TRACKER
M (Days Open) = IF(Closed,0,TODAY()−DateRaised) · N (Discipline Lead) = INDEX/MATCH from Lookup Tables
NCR No. | Discipline | Type | Non-Conformance Description | Location | Raised By | Date Raised | Root Cause | Corrective Action | Responsible | Due Date | Status | Days Open =TODAY()−raised | Disc. Lead =INDEX/MATCH
NCR-001 | Structural | Material | Steel beam flange width 2mm below tolerance — spec 300mm, found 298mm | Zone B Grid 5-6 | M. Berg | 2026-04-02 | Wrong material ordered — spec not checked | Replace beam; update procurement verification | K. Lindqvist | 2026-04-10 | Closed
NCR-002 | Civil | Workmanship | Concrete cover to rebar 18mm vs. 40mm specified | Foundation B3 | J. Hansen | 2026-04-08 | Formwork positioning error | Break out and reinstate; supervisor sign-off | J. Hansen | 2026-04-18 | Closed
NCR-003 | Electrical | Installation | Cable tray support spacing 1200mm vs. 900mm per spec | HV Room | A. Nilsen | 2026-04-12 | Incorrect reading of installation spec | Add intermediate supports; re-inspect all trays | M. Berg | 2026-04-22 | Closed
NCR-004 | Piping | Workmanship | Porosity defect in butt weld — Line P-101 Spool 4 | Zone A Spool 4 | S. Patel | 2026-04-15 | Welder qualification lapse; moisture in electrode | Cut out and re-weld; 100% NDE on 2 adjacent | S. Patel | 2026-04-25 | Closed
NCR-005 | Structural | Workmanship | Bolt torque not achieved — beam-to-column Level 1 | Building 1 L1 | K. Lindqvist | 2026-04-18 | Torque wrench not calibrated | Re-torque all; calibrate tools; 100% re-inspect | K. Lindqvist | 2026-04-28 | Closed
NCR-006 | HVAC | Material | Duct insulation 25mm vs. 40mm specified | Building 1 L2 | L. Andersen | 2026-04-20 | Incorrect material issued from stores | Replace insulation; update material issue checklist | L. Andersen | 2026-05-01 | In Progress
NCR-007 | Structural | Workmanship | Incomplete fusion in fillet weld — Column C7 | Zone C Col C7 | M. Berg | 2026-04-22 | Welder fatigue and inadequate pre-heat | Grind out and re-weld; PWHT review; briefing | M. Berg | 2026-05-05 | In Progress
NCR-008 | Civil | Workmanship | Backfill compaction 91% Proctor vs. 95% minimum | Zone C Layer 3 | J. Hansen | 2026-04-25 | Compaction plant breakdown — work continued | Remove and re-compact; equipment check first | J. Hansen | 2026-05-07 | Open
NCR-009 | Mechanical | Installation | Pump alignment out of tolerance — axial 0.12mm vs. 0.05mm max | Pump Hall P-203 | A. Nilsen | 2026-04-28 | Grouting not cured before alignment | Re-align after 28-day cure; document records | A. Nilsen | 2026-05-10 | Open
NCR-010 | Instrumentation | Installation | Wrong thermocouple type — type J installed vs. K specified | Zone A TI-101 | T. Eriksson | 2026-04-29 | Stores label incorrectly marked | Replace with type K; audit all IDs site-wide | T. Eriksson | 2026-05-08 | Open
NCR-011 | Piping | Workmanship | Gasket material non-conformance — PTFE vs. spiral wound | Zone A Flange F-22 | S. Patel | 2026-04-30 | Substitution without engineering approval | Replace gaskets; issue material deviation form | S. Patel | 2026-05-09 | Open
NCR-012 | Electrical | Installation | Conduit penetration unsealed — missing firestop in firewall | Control Room | M. Berg | 2026-05-01 | Subcontractor unaware of firewall requirement | Apply approved firestop; inspect all penetrations | M. Berg | 2026-05-12 | Open
Formulas:
Days Open =TODAY()−raised = IF([Status]="Closed",0,TODAY()-[Date Raised])
Note on M3: Days Open [FORMULA — do not edit] ──────────────────────────────── = IF(Status = 'Closed', 0, TODAY() − DateRaised) Amber badge: > 14 days open Red badge: > 28 days open Resets to 0 when Status is set to 'Closed'.
Note on N3: Discipline Lead [INDEX/MATCH — auto-filled] ──────────────────────────────── = INDEX(LookupTables!B, MATCH(Discipline, LookupTables!A, 0)) Alternative to VLOOKUP — searches in any column. Updates automatically if Discipline changes.

## Monthly Report
MONTHLY PROGRESS REPORT — Input & Earned Value Analysis
Manual entry: A–H, K–M. Formula-driven: I (SV%) · J (CV%) · N (Disc. Lead = INDEX/MATCH). DASHBOARD SUMIFS pulls from cols A–H.
Month | Discipline | Budget Hours | Actual Hours | Planned % | Actual % | Earned Value (NOK) | Planned Value (NOK) | Schedule Var % =IFERROR((F−E)/E,0) | Cost Var % =IFERROR((G−H)/H,0) | Key Milestones | Issues | Actions Raised | Disc. Lead =INDEX/MATCH | Forecast %
Feb-26 | Civil | 1200 | 1180 | 30% | 28% | 168000 | 180000 |  |  | Excavation complete Zone A | Soft ground — extra dewatering | 0 |  | 34%
Feb-26 | Structural | 800 | 790 | 25% | 26% | 97500 | 93750 |  |  | Steel fabrication 100% complete |  | 0 |  | 32%
Feb-26 | Electrical | 400 | 380 | 15% | 14% | 26600 | 28000 |  |  | Substation foundation ready | Cable delivery delayed 1 week | 2 |  | 20%
Mar-26 | Civil | 1400 | 1450 | 55% | 53% | 318000 | 330000 |  |  | Pile caps Zone A poured | Formwork shortage — mitigated | 1 |  | 59%
Mar-26 | Structural | 1200 | 1150 | 50% | 52% | 312000 | 300000 |  |  | Level 1 steel erection complete |  | 1 |  | 58%
Mar-26 | Electrical | 600 | 580 | 30% | 28% | 84000 | 90000 |  |  | HV cable tray 60% installed |  | 1 |  | 34%
Mar-26 | Mechanical | 500 | 490 | 25% | 26% | 65000 | 62500 |  |  | Pump skids P1–P4 set |  | 0 |  | 32%
Mar-26 | Piping | 800 | 820 | 35% | 38% | 152000 | 140000 |  |  | Fabrication complete; inst. started |  | 0 |  | 44%
Apr-26 | Civil | 1600 | 1580 | 72% | 68% | 408000 | 432000 |  |  | Zone B concrete pours started | 2-day delay — road restrictions | 3 |  | 74%
Apr-26 | Structural | 1400 | 1390 | 65% | 70% | 490000 | 455000 |  |  | Mezzanine steelwork in progress |  | 0 |  | 76%
Apr-26 | Electrical | 900 | 870 | 55% | 52% | 234000 | 247500 |  |  | LV panel wiring started | NCR on cable tray spacing | 0 |  | 58%
Apr-26 | Mechanical | 700 | 690 | 48% | 48% | 168000 | 168000 |  |  | All pump equipment on site | Alignment NCR P-203 | 0 |  | 54%
Apr-26 | Instrumentation | 500 | 490 | 35% | 33% | 82500 | 87500 |  |  | Loop drawings reviewed — 80% | Thermocouple type error | 1 |  | 39%
Apr-26 | Piping | 1000 | 980 | 60% | 62% | 310000 | 300000 |  |  | Hydro test P-101 complete |  | 1 |  | 68%
Apr-26 | HVAC | 600 | 580 | 40% | 38% | 114000 | 120000 |  |  | Ductwork 60% fabricated | Duct insulation NCR | 0 |  | 44%
Apr-26 | Scaffolding | 300 | 295 | 80% | 82% | 73800 | 72000 |  |  | All active scaffolding inspected |  | 1 |  | 88%
MONTHLY EARNED VALUE ANALYSIS · Data sourced from DASHBOARD SUMIFS (cross-sheet reference)
Note on I3: Schedule Variance % [FORMULA — do not edit] ──────────────────────────────── = IFERROR((Actual% − Planned%) / Planned%, 0) Green cell = ahead of schedule (positive) Red cell = behind schedule (negative) Referenced by DASHBOARD SUMIFS monthly summary.
Note on J3: Cost Variance % [FORMULA — do not edit] ──────────────────────────────── = IFERROR((EV − PV) / PV, 0) Green = EV > PV (under budget) Red = EV < PV (over budget) CPI chart on DASHBOARD uses Dashboard SUMIFS of this data.
Note on N3: Discipline Lead [INDEX/MATCH — auto-filled] ──────────────────────────────── = INDEX(LookupTables!B:B, MATCH(Discipline, LookupTables!A:A, 0)) Updates automatically when Discipline cell changes.

## Data Validation Log
DATA VALIDATION & QUALITY LOG
PURPOSE: Log all data quality issues found during weekly/monthly validation sweeps. Every anomaly must be logged before correction to maintain a full audit trail. All Open items must be resolved before submission to client reporting.
Log ID | Date Found | Data Source | Field / Column | Error Type | Error Description | Responsible | Severity | Action Taken | Status | Date Resolved
VAL-001 | 2026-04-28 | Weekly Progress | Actual % | Missing Data | Actual % not entered for Instrumentation W17 | T. Eriksson | High | Followed up; data entered same day | Resolved | 2026-04-28
VAL-002 | 2026-04-28 | Risk Register | Review Date | Stale Data | 6 risks with review date passed — not updated for 2+ weeks | S. Patel | Medium | All owners notified; register updated W18 | Resolved | 2026-04-29
VAL-003 | 2026-04-29 | Action Item Log | Due Date | Missing Data | 3 actions with no due date assigned | J. Hansen | High | Dates confirmed in coord meeting W18 | Resolved | 2026-04-29
VAL-004 | 2026-04-29 | Monthly Report | Actual Hours | Out of Range | HVAC actual hours 5200 entered (budget 600) — data entry error | L. Andersen | Critical | Corrected to 580h; source timesheet confirmed | Resolved | 2026-04-30
VAL-005 | 2026-04-30 | NCR Tracker | Root Cause | Missing Data | NCR-008, 009, 010 missing root cause entries | M. Berg | Medium | Root causes added after investigation reports | Resolved | 2026-05-01
VAL-006 | 2026-04-30 | Weekly Progress | Week No. | Wrong Format | Week entered as '18W' instead of integer 18 | R. Kowalski | Low | Corrected; format reminder sent to all leads | Resolved | 2026-05-01
VAL-007 | 2026-05-01 | Monthly Report | EV Calc | Logic Error | Earned Value = −12000 for Piping Feb-26 — formula error | S. Patel | High | Formula corrected; cross-checked against cost plan | Resolved | 2026-05-01
VAL-008 | 2026-05-02 | Action Item Log | Status | Stale Data | 4 actions marked Open with due date passed | J. Hansen | High | Status updated to Overdue; owners notified | Resolved | 2026-05-02
VAL-009 | 2026-05-03 | Risk Register | Risk Score | Logic Error | RSK-006 score = 0 — Probability and Impact were blank | S. Patel | Medium | Values entered; level updated to Medium (score = 8) | Resolved | 2026-05-03
VAL-010 | 2026-05-04 | Weekly Progress | Responsible | Missing Data | 2 activities have no Responsible person assigned | J. Hansen | Medium | XLOOKUP auto-filled; manual review pending | Open
VAL-011 | 2026-05-04 | NCR Tracker | Date Closed | Logic Error | NCR-006 status=Closed but Date Closed cell is empty | M. Berg | High | Correction in progress | Open
VAL-012 | 2026-05-04 | Monthly Report | Forecast % | Out of Range | Forecast 112% for Civil Apr-26 — cannot exceed 100% | J. Hansen | Medium | Capped at 100%; formula review in progress | Open

## Lookup Tables
LOOKUP TABLES — Reference Data for Formula Calculations
Powers VLOOKUP · XLOOKUP · INDEX/MATCH across all sheets. Do not rename or delete this sheet.
TABLE 1 · Discipline → Lead Person (VLOOKUP / XLOOKUP / INDEX-MATCH reference) |  |  |  | TABLE 2 · Risk Score Reference (IFS formula band reference)
Discipline | Lead Person | Dept. Code | Email | Min Score | Max Score | Level | SLA Response
Civil | J. Hansen | CIV | j.hansen@project.com | 15 | 25 | High | Immediate action
Structural | K. Lindqvist | STR | k.lindqvist@project.com | 8 | 14 | Medium | Action within 14 days
Electrical | M. Berg | ELE | m.berg@project.com | 1 | 7 | Low | Monitor monthly
Mechanical | A. Nilsen | MEC | a.nilsen@project.com
Instrumentation | T. Eriksson | INS | t.eriksson@project.com
Piping | S. Patel | PIP | s.patel@project.com
HVAC | L. Andersen | HVA | l.andersen@project.com
Scaffolding | R. Kowalski | SCA | r.kowalski@project.com
All | J. Hansen | ALL | j.hansen@project.com
TABLE 3 · Status Definitions & Dropdown Values |  |  |  | TABLE 4 · Formula Index — Where Each Advanced Function Is Used
Status | Applies To | Final? | Description | Sheet | Column | Function | Purpose
Open | Actions / Risks / NCRs | No | Raised, no action started | Weekly Progress | Variance % |  | Auto variance
In Progress | Actions / NCRs | No | Work underway | Weekly Progress | Status | IF nested | Auto status logic
Closed | All | Yes | Fully resolved and verified | Weekly Progress | Responsible | XLOOKUP | From Lookup Tables
Overdue | Actions | No | Past due date — escalate | Risk Register | Risk Score |  | Auto P×I
Escalated | Risks | No | Elevated to senior management | Risk Register | Risk Level | IF nested | From score
Mitigated | Risks | No | Mitigation complete; monitoring | Action Item Log | Responsible | VLOOKUP | From Lookup Tables
On Hold | Actions | No | Blocked — awaiting input | Action Item Log | Days Overdue | IF/TODAY() | Live days past due
|  |  |  | NCR Tracker | Days Open | IF/TODAY() | Live days since raised
|  |  |  | NCR Tracker | Discipline Lead | INDEX/MATCH | From Lookup Tables
|  |  |  | Monthly Report | Schedule Var % | IFERROR/() | Auto SV%
|  |  |  | Monthly Report | Cost Var % | IFERROR/() | Auto CV%
|  |  |  | Monthly Report | Discipline Lead | INDEX/MATCH | From Lookup Tables
|  |  |  | DASHBOARD | All KPIs | COUNTIF | Live from data sheets
|  |  |  | DASHBOARD | Discipline table | AVERAGEIF | Live pull per discipline
|  |  |  | DASHBOARD | Monthly summary | SUMIFS | Multi-criteria totals

## Instructions & Guide
WORKBOOK GUIDE — Construction Project Data Management System
Sheet directory, formula reference, color legend, ID conventions, and usage workflow.
SHEET DIRECTORY
Sheet | Purpose | Entry Columns | Key Formulas | Update Frequency
Lookup Tables | Reference tables — powers all lookup formulas | Update when personnel changes | N/A | When team changes
DASHBOARD | Live project health — KPIs, progress, risk, actions, EV | Read-only (formula-driven) | COUNTIF/S, AVERAGEIF, SUMIFS | Auto on file open
Weekly Progress | Planned vs. actual % per activity per week | G (Planned%) and H (Actual%) | IF, XLOOKUP | Weekly — by Friday
Risk Register | Risk log with P×I matrix and auto level | All except G, H | E×F, nested IF | Weekly minimum
Action Item Log | All meeting action items with status tracking | All except F, N | VLOOKUP, IF/TODAY() | After each meeting
NCR Quality Tracker | Non-conformance full lifecycle | All except M, N | TODAY()−date, INDEX/MATCH | As NCRs arise
Monthly Report | Budget vs. actual + Earned Value analysis | A–H, K–M | SV/CV formulas, INDEX/MATCH, SUMIFS | 2nd working day
Data Validation Log | Data quality issues audit trail | All columns | Manual log | During validation sweep
FORMULA REFERENCE
Function | Sheet — Column | Example | Purpose | Version
COUNTIF | Dashboard — KPI tiles |  | Count matching single criterion | All
COUNTIFS | Dashboard — discipline table |  | Count matching multiple criteria | 2007+
AVERAGEIF | Dashboard — discipline % |  | Average matching one criterion | 2007+
SUMIFS | Dashboard — monthly summary |  | Sum matching multiple criteria | 2007+
VLOOKUP | Action Log — Responsible col |  | Lookup value in first column of table | All
XLOOKUP | Weekly Progress — Responsible |  | Flexible; searches any direction | Excel 365
INDEX/MATCH | NCR & Monthly — Disc. Lead |  | Flexible alternative to VLOOKUP | All
IF nested | Weekly Progress — Status col |  | Multi-branch conditional logic | All
IFERROR | All formula columns |  | Return fallback if formula errors | 2007+
TODAY() | Action Log — Days Overdue |  | Current date; updates on open | All
COLOR & BADGE LEGEND
| Green badge | Completed · Closed · Resolved · Ahead · Low risk
| Blue badge | Open · On Track · Mitigated · Material
| Amber badge | In Progress · Medium · Workmanship · Warning
| Red badge | Overdue · High · Behind · Critical · Escalated
| Gray badge | Not Started · On Hold · Neutral / N/A
| Teal badge | Installation type NCRs
| Surface row | Alternating data row background (barely visible)
| Dark header | Column headers and section headers — uniform charcoal
| Ink title | Sheet titles — near-black